## Sheet1
Team Name | ezHealth
Topic | Healthy Living
Team Members
Name: | Role:
Rehan Theiveehathasan | Programmer (Void updates)
Edwin Do | Project Manager
Ridhwan Chowdhury | Front End Interface
Brian Kibazohi | Programmer (Determining Algorithms and Searching/Sorting got the DataSet
Timothy Chen | Log Admin/Front End Support
Timestop | Originator | Type | Task ID | Status | Comments | Supporting Document
190225T1530 | All | Task | 1 | Completed | Selecting Project | N/A
190225T1530 | All | Task | 1 | Completed | Distribution | N/A
190228T2030 | All | Task | 1 | Completed | Finding Data Set(food prices) | N/A
190228T2030 | Rehan | Task | 1 | Completed | Producing Graph Alogorithm idea | N/A
190305T1130 | Edwin | Task | 1 | Completed | Reading in Data set(food) | N/A
190312T1230 | Rehan | Task | 1 | Completed | Creating Rough API | N/A
190313T1520 | Ridhwan | Task | 1 | Cancelled | Finding Data Set(Stores) | N/A
190303T2000 | All | Meeting | 1 | Completed | Determing Milstones | Milestone_1.doc
193010T1530 | All | Meeting | 1 | Completed | Roles Finalized